## Sheet1
WBS # | Name / Title | Type | Start Date | End Date | Estimated Hours | Actual Hours | Percent Complete | Resources | Predecessors | Notes | Comments | Task Color
1 | VisualizaÃ§Ã£o geral do desenvolvimento | project | 2019-01-14 | 2019-05-10 | 0 | 0 | 45.67
1.1 | Todas tarefas gerenciÃ¡veis | group | 2019-01-14 | 2019-05-10 | 0 | 0 | 45.67
1.1.1 | DefiniÃ§Ã£o de banco de dados | task | 2019-01-14 | 2019-01-14 | 0 | 0 | 100 | Erick J P |  |  |  | red1
1.1.2 | EstruturaÃ§Ã£o da Nuvem-Client | task | 2019-01-14 | 2019-01-14 | 0 | 0 | 100 | Rafael |  |  |  | red1
1.1.3 | Desenhar soluÃ§Ã£o completa do sistema | task | 2019-01-14 | 2019-01-14 | 0 | 0 | 100 | Erick J P |  |  |  | red1
1.1.4 | Multi conexÃµes dinÃ¢micas - Nuvem-Server | task | 2019-01-14 | 2019-01-14 | 0 | 0 | 100 | Rafael |  |  |  | red1
1.1.5 | EstruturaÃ§Ã£o da Nuvem-Server | task | 2019-01-14 | 2019-01-14 | 0 | 0 | 100 | Rafael |  |  |  | red1
1.1.6 | ComunicaÃ§Ã£o Nuvem-Client com Nuvem-Server | task | 2019-01-14 | 2019-01-14 | 0 | 0 | 100 | Rafael |  |  |  | red1
1.1.7 | EstruturaÃ§Ã£o da API que receberÃ¡ requisiÃ§Ãµes dos clientes | task | 2019-01-14 | 2019-01-14 | 0 | 0 | 100 | Erick J P |  |  |  | red1
1.1.8 | Criar padrÃ£o de comunicaÃ§Ã£o entre os coletores com o coletor master | task | 2019-01-14 | 2019-01-14 | 0 | 0 | 100 | Erick J P |  |  |  | red1
1.1.9 | AutenticaÃ§Ã£o e permissionamento da aplicaÃ§Ã£o | task | 2019-01-14 | 2019-01-14 | 0 | 0 | 100 | Rafael |  |  |  | red1
1.1.10 | Modelar comunicaÃ§Ãµes dos coletores, coletores masters com a API que comunicarÃ¡ com os coletores | task | 2019-01-14 | 2019-01-14 | 0 | 0 | 100 | Erick J P |  |  |  | red1
1.1.11 | Containers do SQL Server | task | 2019-01-14 | 2019-01-14 | 0 | 0 | 100 | Rafael |  |  |  | red1
1.1.12 | EstruturaÃ§Ã£o da API | task | 2019-01-14 | 2019-01-14 | 0 | 0 | 100 | Erick J P |  |  |  | blue2
1.1.13 | Implementar multi conexÃµes por clientes | task | 2019-01-14 | 2019-01-14 | 0 | 0 | 100 | Rafael |  |  |  | green3
1.1.14 | ImplementaÃ§Ã£o da estrutura e template do client | task | 2019-01-14 | 2019-01-14 | 0 | 0 | 100 | Rafael |  |  |  | green3
1.1.15 | #7 - Tela de PapÃ©is | task | 2019-01-14 | 2019-01-14 | 0 | 0 | 100 | Rafael |  |  |  | green3
1.1.16 | #14 - ImplementaÃ§Ã£o da estrutura do server | task | 2019-01-14 | 2019-01-14 | 0 | 0 | 100 | Rafael |  |  |  | green3
1.1.17 | #15 - ComunicaÃ§Ã£o Nuvem-Client com Nuvem-Server | task | 2019-01-14 | 2019-01-14 | 0 | 0 | 100 | Rafael |  |  |  | green3
1.1.18 | #16 - AutenticaÃ§Ã£o e permissionamento | task | 2019-01-14 | 2019-01-14 | 0 | 0 | 100 | Rafael |  |  |  | green3
1.1.19 | #17 - Containers do SQL Server | task | 2019-01-14 | 2019-01-14 | 0 | 0 | 100 | Rafael |  |  |  | green3
1.1.20 | Disponibilizar lista de servidores master | task | 2019-01-14 | 2019-01-14 | 0 | 0 | 100 | Erick J P |  |  |  | blue2
1.1.21 | Consultar os servidores master cadastrados | task | 2019-01-15 | 2019-01-16 | 0 | 0 | 100 | Erick J P | 1.1.20 |  |  | green1
1.1.22 | Tela - Cadastro dos servidores master | task | 2019-01-17 | 2019-01-21 | 0 | 0 | 100 | Erick J P | 1.1.21 |  |  | green1
1.1.23 | Gravar localmente (coletor master) | task | 2019-01-22 | 2019-01-24 | 0 | 0 | 100 | Erick J P |  |  |  | green1
1.1.24 | Descoberta de discos | task | 2019-01-25 | 2019-01-28 | 0 | 0 | 80 | Erick J P | 1.1.22,1.1.23 |  |  | green1
1.1.25 | Descoberta de rede | task | 2019-01-29 | 2019-01-30 | 0 | 0 | 0 | Erick J P | 1.1.24 |  |  | green1
1.1.26 | Descoberta de aplicaÃ§Ãµes | task | 2019-01-31 | 2019-02-01 | 0 | 0 | 90 | Erick J P | 1.1.25 |  |  | green1
1.1.27 | Listagem de telas e requisitos para o desenvolvimento das mesmas | task | 2019-01-29 | 2019-02-01 | 0 | 0 | 100 | Rafael |  |  |  | red1
1.1.28 | Estruturar grupos de acessos e permissÃ£o no bitbuket | task | 2019-02-01 | 2019-02-01 | 0 | 0 | 100 | Rafael |  |  |  | red1
1.1.29 | #20 - Criar arquivo readme | task | 2019-02-04 | 2019-02-04 | 0 | 0 | 100 | Rafael |  |  |  | green3
1.1.30 | #7 - Criar arquivo readme.md | task | 2019-02-05 | 2019-02-05 | 0 | 0 | 100 | Rafael | 1.1.29 |  |  | blue3
1.1.31 | Modelagem do banco de dados | task | 2019-02-04 | 2019-02-08 | 0 | 0 | 100 | Erick J P, Rafael | 1.1.26,1.1.27 |  |  | red1
1.1.32 | Identificar custos operacionais de cada cliente | task | 2019-02-06 | 2019-02-08 | 0 | 0 | 40 | Erick J P |  |  | [InserÃ§Ã£o de um novo cliente API Node JS - Aumento Processamento - Aumento MemÃ³ria - Aumento Dados de entrada (Coletores master) - Aumento Dados de saÃ­da (Banco de dados Cliente) Banco de dados do Cliente - Nova mÃ¡quina - Armazenamento - Processamento - MemÃ³ria - Dados de entrada (API NodeJS) - Dados de saÃ­da (API PHP) Banco de dados da Revenda - Aumento Processamento - Aumento MemÃ³ria - Aumento de Armazenamento Banco de dados da OWL - Aumento Processamento - Aumento MemÃ³ria - Aumento de Armazenamento API PHP - Aumento Processamento - Aumento MemÃ³ria - Aumento Dados de entrada (Banco de dados Cliente / Revendas / OWL) - Aumento Dados de saÃ­da (React JS) -- by: Erick J P on 2019-02-25T12:30:44Z] [Falta identificar a quantificaÃ§Ã£o (R$) que representa o aumento dos recursos com base no formato de cobranÃ§as -- by: Erick J P on 2019-02-25T12:32:01Z] | red1
1.1.33 | PreparaÃ§Ã£o do ambiente de testes | task | 2019-02-11 | 2019-02-13 | 0 | 0 | 60 | Erick J P, Rafael | 1.1.31 |  |  | red1
1.1.34 | Criar ambiente de background na nuvem | task | 2019-02-14 | 2019-02-19 | 0 | 0 | 80 | Erick J P | 1.1.33 |  |  | red1
1.1.35 | Pesquisar ferramenta de WIki | task | 2019-02-15 | 2019-02-21 | 0 | 0 | 50 | Erick J P, Rafael |  |  | [NÃ£o encontrado a ferramenta, porÃ©m utilizado o OneNote para armazenar a base de conhecimento atualmente -- by: Erick J P on 2019-02-25T12:29:47Z] [https://onedrive.live.com/view.aspx?resid=94BA8AFA6FD4ED42%21416041&id=documents&wd=target%28Base%20de%20Conhecimento.one%7C299023AA-CC12-489C-A5D5-69380BBF6F6B%2F%29 onenote:https://d.docs.live.net/94ba8afa6fd4ed42/Documentos/Startup%20-%20Monitoramento/Base%20de%20Conhecimento.one#section-id={299023AA-CC12-489C-A5D5-69380BBF6F6B}&end -- by: Erick J P on 2019-02-25T12:30:01Z] | red1
1.1.36 | Gravar ConfiguraÃ§Ãµes bÃ¡sicas | task | 2019-02-21 | 2019-02-22 | 0 | 0 | 100 | Erick J P | 1.1.34 |  |  | green1
1.1.37 | Salvar configuraÃ§Ãµes no banco de dados | task | 2019-02-25 | 2019-02-26 | 0 | 0 | 80 | Erick J P | 1.1.36 |  |  | green1
1.1.38 | RecepÃ§Ã£o e gravaÃ§Ã£o de configuraÃ§Ã£o master | task | 2019-02-27 | 2019-03-01 | 0 | 0 | 30 | Erick J P | 1.1.37 |  |  | blue2
1.1.39 | Disponibilizar configuraÃ§Ã£o master | task | 2019-03-04 | 2019-03-07 | 0 | 0 | 40 | Erick J P | 1.1.38 |  |  | blue2
1.1.40 | Buscar equipamentos SNMP | task | 2019-03-08 | 2019-03-12 | 0 | 0 | 0 | Erick J P | 1.1.39 |  |  | green1
1.1.41 | Buscar itens monitorados | task | 2019-03-13 | 2019-03-13 | 0 | 0 | 100 | Erick J P | 1.1.40 |  |  | green1
1.1.42 | Coletar dados Windows - CPU | task | 2019-03-14 | 2019-03-14 | 0 | 0 | 0 | Erick J P | 1.1.41 |  |  | green1
1.1.43 | RecepÃ§Ã£o e gravaÃ§Ã£o de dados dos itens | task | 2019-03-15 | 2019-03-19 | 0 | 0 | 0 | Erick J P | 1.1.42 |  |  | blue2
1.1.44 | Dados podendo ser utilizado na API | milestone | 2019-03-20 | 2019-03-20 | 0 | 0 | 0 |  | 1.1.43 |  |  | blue2
1.1.45 | Coletar dados Windows - MemÃ³ria | task | 2019-03-20 | 2019-03-20 | 0 | 0 | 0 | Erick J P | 1.1.43 |  |  | green1
1.1.46 | Coletar dados Windows - Disponibilidade | task | 2019-03-21 | 2019-03-21 | 0 | 0 | 0 | Erick J P | 1.1.45 |  |  | green1
1.1.47 | Coletar dados Windows - Logs | task | 2019-03-22 | 2019-03-25 | 0 | 0 | 0 | Erick J P | 1.1.46 |  |  | green1
1.1.48 | Coletar dados Windows - Armazenamento | task | 2019-03-26 | 2019-03-26 | 0 | 0 | 0 | Erick J P | 1.1.47 |  |  | green1
1.1.49 | Coletar dados Windows - Windows Update | task | 2019-03-27 | 2019-03-27 | 0 | 0 | 0 | Erick J P | 1.1.48 |  |  | green1
1.1.50 | Coletar dados Windows - AplicaÃ§Ãµes | task | 2019-03-28 | 2019-03-29 | 0 | 0 | 0 | Erick J P | 1.1.49 |  |  | green1
1.1.51 | Criptografia de dados para envio Ã API | task | 2019-04-01 | 2019-04-04 | 0 | 0 | 0 | Erick J P | 1.1.50 |  | [Fazer a criptografia na origem dos dados -- by: Erick J P on 2019-02-04T12:59:55Z] | green1
1.1.52 | Descriptografar dados na API | task | 2019-04-05 | 2019-04-08 | 0 | 0 | 0 | Erick J P | 1.1.51 |  |  | blue2
1.1.53 | Criptografia de dados para envio ao coletor | task | 2019-04-09 | 2019-04-10 | 0 | 0 | 0 | Erick J P | 1.1.52 |  |  | blue2
1.1.54 | Consultar a conexÃ£o de banco de dados | task | 2019-04-10 | 2019-04-12 | 0 | 0 | 0 | Erick J P |  |  |  | blue2
1.1.55 | Envio de dados para API NodeJS | task | 2019-04-15 | 2019-04-16 | 0 | 0 | 0 | Erick J P | 1.1.54 |  |  | green1
1.1.56 | Criar instalador do coletor - Incluir banco de dados | task | 2019-04-17 | 2019-04-19 | 0 | 0 | 0 | Erick J P | 1.1.55 |  |  | blue2
1.1.57 | Coletar dados do Mikrotik | task | 2019-04-22 | 2019-04-30 | 0 | 0 | 0 | Erick J P | 1.1.56 |  |  | blue2
1.1.58 | Coletar dados Linux - Disponibilidade | task | 2019-05-01 | 2019-05-01 | 0 | 0 | 0 | Erick J P | 1.1.57 |  |  | green1
1.1.59 | Coletar dados Linux - CPU | task | 2019-05-02 | 2019-05-02 | 0 | 0 | 0 | Erick J P | 1.1.58 |  |  | green1
1.1.60 | Coletar dados Linux - MemÃ³ria | task | 2019-05-03 | 2019-05-03 | 0 | 0 | 0 | Erick J P | 1.1.59 |  |  | green1
1.1.61 | Coletar dados Linux armazenamento | task | 2019-05-06 | 2019-05-08 | 0 | 0 | 0 | Erick J P | 1.1.60 |  |  | green1
1.1.62 | Coletar dados Linux - Logs | task | 2019-05-09 | 2019-05-10 | 0 | 0 | 0 | Erick J P | 1.1.61 |  |  | green1
1.1.63 | #12 - CriaÃ§Ã£o de tabelas do banco de dados | task | 2019-02-15 | 2019-02-18 | 0 | 0 | 100 | Rafael |  |  |  | blue3
1.1.64 | #13 - Automatizar build | task | 2019-02-19 | 2019-02-25 | 0 | 0 | 100 | Rafael | 1.1.63 |  |  | blue3
1.1.65 | #22 - Automatizar build | task | 2019-02-25 | 2019-02-25 | 0 | 0 | 100 | Rafael |  |  |  | green3
1.1.66 | #8 - Controller de empresa | task | 2019-02-25 | 2019-02-25 | 0 | 0 | 100 | Rafael | 1.1.64 |  |  | blue3
1.1.67 | #5 - Default filter para cliente | task | 2019-02-25 | 2019-02-25 | 0 | 0 | 100 | Rafael | 1.1.66 |  |  | blue3
1.1.68 | #16 - Alterar cliente logado | task | 2019-02-26 | 2019-02-26 | 0 | 0 | 100 | Rafael | 1.1.67 |  |  | blue3
1.1.69 | #21 - Selecionar cliente logado | task | 2019-02-26 | 2019-02-26 | 0 | 0 | 100 | Rafael | 1.1.68 |  |  | green3
1.1.70 | Pesquisar meio para bloqueio de permissÃ£o especÃ­fica de um dado | task | 2019-02-27 | 2019-02-27 | 0 | 0 | 0 | Rafael | 1.1.69 |  |  | red1
1.1.71 | #15 - Adicionar SoftDelete no sistema | task | 2019-02-28 | 2019-02-28 | 0 | 0 | 100 | Rafael | 1.1.70 |  |  | blue3
1.1.72 | #17 - Trocar a chave ID por UUID | task | 2019-03-01 | 2019-03-01 | 0 | 0 | 100 | Rafael | 1.1.71 |  |  | blue3
1.1.73 | #2 - Controller de Grupos | task | 2019-03-01 | 2019-03-01 | 0 | 0 | 100 | Rafael | 1.1.72 |  |  | blue3
1.1.74 | #18 - PublicaÃ§Ã£o pelo Jenkins | task | 2019-03-08 | 2019-03-08 | 0 | 0 | 0 | Rafael |  |  |  | blue3
1.1.75 | #8 - Tela de Grupos | task | 2019-03-04 | 2019-03-05 | 0 | 0 | 100 | Rafael | 1.1.73 |  |  | green3
1.1.76 | #1 - Controller de UsuÃ¡rios | task | 2019-03-06 | 2019-03-06 | 0 | 0 | 100 | Rafael | 1.1.75 |  |  | blue3
1.1.77 | #6 - Tela de UsuÃ¡rios | task | 2019-03-07 | 2019-03-07 | 0 | 0 | 100 | Rafael | 1.1.76 |  |  | green3
1.1.78 | #19 - NavegaÃ§Ã£o por abas | task | 2019-03-08 | 2019-03-11 | 0 | 0 | 0 | Rafael | 1.1.77 |  |  | green3
1.1.79 | #4 - Tela Inicial | task | 2019-03-12 | 2019-03-15 | 0 | 0 | 100 | Rafael | 1.1.78 |  |  | green3
1.1.80 | Disponibilidade de testes | milestone | 2019-03-18 | 2019-03-18 | 0 | 0 | 0 |  | 1.1.79 |  |  | blue2
1.1.81 | #9 - EstruturaÃ§Ã£o e cadastro manual de empresas | task | 2019-03-18 | 2019-03-18 | 0 | 0 | 0 | Rafael | 1.1.79 |  |  | blue3
1.1.82 | #3 - Controller de Regras | task | 2019-03-19 | 2019-03-20 | 0 | 0 | 0 | Rafael | 1.1.81 |  |  | blue3
1.1.83 | #10 - Controller para recepÃ§Ã£o de leitura | task | 2019-03-21 | 2019-03-22 | 0 | 0 | 0 | Rafael | 1.1.82 |  |  | blue3
1.1.84 | #11 - Desenvolver aÃ§Ãµes para as regras | task | 2019-03-25 | 2019-03-26 | 0 | 0 | 0 | Rafael | 1.1.83 |  |  | blue3
1.1.85 | #9 - Tela de Regras | task | 2019-03-27 | 2019-04-02 | 0 | 0 | 0 | Rafael | 1.1.84 |  |  | green3
1.1.86 | #6 - Controller de IC - Incidentes | task | 2019-04-03 | 2019-04-04 | 0 | 0 | 0 | Rafael | 1.1.85 |  |  | blue3
1.1.87 | #12 - Tela de IC - Incidente | task | 2019-04-05 | 2019-04-10 | 0 | 0 | 0 | Rafael | 1.1.86 |  |  | green3
1.1.88 | #10 - Tela de PlantÃ£o | task | 2019-04-11 | 2019-04-16 | 0 | 0 | 0 | Rafael | 1.1.87 |  |  | green3
1.1.89 | #4 - Controller de ConfiguraÃ§Ãµes | task | 2019-04-17 | 2019-04-18 | 0 | 0 | 0 | Rafael | 1.1.88 |  |  | blue3
1.1.90 | #11 - Tela de ConfiguraÃ§Ãµes | task | 2019-04-19 | 2019-04-23 | 0 | 0 | 0 | Rafael | 1.1.89 |  |  | green3
1.1.91 | Tela de Valores | task | 2019-04-24 | 2019-04-30 | 0 | 0 | 0 | Rafael | 1.1.90 |  |  | green3
1.1.92 | #23 - PublicaÃ§Ã£o Jenkins | task |  |  | 0 | 0 | 0 |  |  |  |  | blue2
1.1.93 | AÃ§Ãµes - Gatilho para jogar numa tela de listagem | task |  |  | 0 | 0 | 0 |  |  |  |  | blue2